## Test summary report
Tester | HTThuận, TĐTùng, TTLợi, HHNam, LTKOanh
Date | 2024-08-28

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | Unable to use payment method with debit/credit card | After fill in the necessary information in payment with debit/credit card and press Submit button, the system does not have any reactions | UC05 | Moderate | Trần Đức Tùng | 22/08/2024 | Open | Still not fix
B002 | The signup information is lack of avatar picture, but still acceptable | Do not upload any file, but after pressing Submit, the account is acceptable to be created. | UC01 | Moderate | Trần Đức Tùng | 18/08/2024 | Closed | Fixed. Now the account cannot be created without uploading the file.
B003 | The product is out-of-stock, but can be added to shopping cart | The product is out of stock in database, but we can still choose that product and add it to the shopping cart for payment | UC03 | High | Huỳnh Nhật Nam | 17/8/2024 | Closed | Fixed. Cannot buy any product that its quantity is 0.
B004 | Login with a wrong email address | The text popped out for the user to notice the error is not right | UC02 | Low | Lê Trần Kim Oanh | 28/08/2024 | Closed | Fixed.
B005 | Can create a product without uploading an image. | At the create product tab, we can still upload a product without uploading an image of that product | UC04 | Moderate | Lê Trần Kim Oanh | 28/08/2024 | closed | Fixed.
Note on D1: ====== ID#AAABUynpD90 Vu V. Nguyen (2024-08-28 06:23:15) Function ID of the function where the defect is found
Note on E1: ====== ID#AAABUynpD94 Vu V. Nguyen (2024-08-28 06:23:15) High, Medium, or Low
Note on F1: ====== ID#AAABUynpD9w Vu V. Nguyen (2024-08-28 06:23:15) Name of the tester who reports the defect
Note on H1: ====== ID#AAABUynpD9s Vu V. Nguyen (2024-08-28 06:23:15) Open or Closed